## Sheet1
| Sales Order #: | 18200 |  |  |  | Rep: | Mike
| Project Name: | Powder River Coal Peabody |  |  |  | PO# | 300154024
Brief Description:
Install Welding Booths and arms, Fan
|  | Duct Drawings Submitted: |  |  |  | NO
|  | Customized Products: |  |  |  | NO
|  | Contractors Needed: |  |  |  | YES | Tool Inspection
EQUIPMENT | Manufacturer | Product | PO | AVI Cost | Quantity | Total | Quoted by Sales | Margin
| SmartVent | Booths/Arms | 4217 | 12768 | 1 | 12768 | 20880 | 32.49%
| Frommelt | Curtains | 4317 | 221.31 | 6 | 1327.86
| Cincinnati Fan | Fan | 4336 | 3183 | 1 | 3183 | 5879 | 45.86%
| K&B Duct | Duct | 4472 | 1375.17 | 1 | 1375.17 | 4269 | 22.69%
| Fastenal | Pipe Flash | 4318 | 213.77 | 1 | 213.77
| K&B Duct | Duct | 4372 | 198.92 | 1 | 198.92
| Materials - Duct From Avani |  | 0 | 2529.89 | 1 | 2529.89
| Material - Other |  |  | 95.4 | 1 | 95.4
| Duct Returned |  |  | 1112.77 |  | 1112.77
| TOTALS |  |  |  |  | 20579.24 | 31028 | 33.68%
| Project Start / Finish Dates: |  |  | 5/9/12-5/11/12
| Location: | Gilette, WY
| Crew Leader: | Rodney
LABOR | Tasks |  |  | Avani Costs | Quantity | Total | Quoted | Margin
| Labor - Travel Cost / Man Hour |  |  | 62 | 26 | 1612 | 5090 | 6.817%
| Labor - On-site / Man Hour |  |  | 62 | 50.5 | 3131
| Labor - Other Costs |  |  |  |  | 0
| Airfare: yes |  |  | 682.8 | 1 | 682.8
Total Overnight Stays:
Other -
| TOTALS |  |  |  |  | 5425.8 | 5090 | -6.597%
| JOB TOTAL |  |  |  |  | 26005.04 | 36118 | 28%
Note on E10: Cynthia: Add 15% for container shipments
Note on E28: Cynthia: use 75 for 1 man crew
Note on F27: Cynthia: x2 men
Note on F28: Cynthia: x2 men

## Sheet2
28 | 90 | 2520
2 | 165 | 330
5 | 18.315 | 91.575
1 | 36.33 | 36.33
17 | 15.6375 | 265.8375
2 | 31.7775 | 63.555
2 | 25.6425 | 51.285
3358.5825